## Aims
VW Comms Plan
Comms Plan Overall Aim
To maximise the usage of Virtual Wallet by all stakeholders
Comms Plan Rationale
To maximise the usage of Virtual Wallet by all stakeholders…in order to promote a personalised care model that increases the number of DPs/PHBs and saves the LA/ICB money by harnessing the benefits of DPs/PHBs whilst reducing the admin burden associated with them
Comms Plan Objectives
1. Ensure that all relevant staff are aware of Virtual Wallet and what it offers
2. Ensure that all local partner staff (DPSS, VCSE) are aware of Virtual Walet and what it offers
3. Increase traffic to the My Virtual Wallet site by promoting it across mutiple (low/no cost) channels
4. Increase the number of people with a Virtual Wallet account by making it 'business as usual'
5. Ensure that providers and PAs are aware of Virtual Wallet and are onboarded where appropriate
Comms Plan Evaluation Metrics
A. Increase in the number of people with a Virtual Wallet account
B. Increase in the number of people with a DP/PHB overall
C. Increase in number of care management staff who feel confident about promoting DPs/PHBs generally and Virtual Wallet specifically
Comms Team
PPL:
LA/ICB:
Other:

## Comms Plan
VW Comms Plan |  | Audience |  |  |  | Mechanism | [5 empty] | Implementation
Ref | Activity | Public | Staff | 3rd Sector | SMT | Email | Social media | My VW site | Other | Notes | Who | When | Resource / Cost | Status
1. General
1.1 | Setup Comms Team and agree Aims and Plan | Y | Y | Y |  |  |  |  | Y
1.2 | Agree 2-3 key messages for this locality | Y | Y | Y |  |  |  |  | Y | Repeat!
1.3 | Create local entry on MyVirtualWallet website | Y | Y | Y |  |  |  | Y |  | PPL responsibility | PPL
1.4 | Tailor MyVW site to locality (info, contacts) | Y | Y | Y |  |  |  | Y |  | PPL and LA/ICB Project Lead
1.5 | Update LA/ICB website DP/PHB sction to direct to MyVW site | Y | Y | Y |  |  |  | Y | Y | See Comms Hub for suggestions
1.6 | Obtain supply of hard-copy postcards and merch | Y | Y | Y |  |  |  |  | Y |  | PPL
1.7 | Comms standing item on Project Team / Account Man't meeting | Y | Y | Y |  |  |  |  | Y
1.8 | Share one 'good news' story per month | Y | Y | Y | Y | Y | Y | Y
1.9 | Review comms approach & collateral of other PPL clients | Y | Y | Y |  |  |  |  | Y | Comms Hub
2. Internal (LA/ICB)
2.1 | Staff launch events (webinars, existing forums?) |  | Y | [5 empty] | Y | Use std slides from Comms Hub
2.2 | Schedule refesher events |  | Y | [5 empty] | Y | Quarterly or on agenda of existing
2.3 | Circulate link to MyVW website |  | Y |  |  | Y |  | Y
2.4 | Circulate link to 'VW for LAs/ICBs' video |  | Y |  |  | Y |  | Y |  | 3 min video aimed at LAs/ICBs
2.5 | Circulate link to 'VW for Individuals' video | Y | Y | Y |  | Y |  | Y |  | 3 min video aimed at individuals
2.6 | Circulate links to 'VW Shorts' videos | Y | Y | Y |  | Y | Y
2.7 | Compile & circulate local 'Top 10' and 'FAQs' docs |  | Y |  |  | Y |  |  |  | aka 'Briefing Note'
2.8 | Circulate PPL 'How to explain VW' flier |  | Y |  |  | Y |  |  |  | To help frontline staff
2.9 | Consider appointing 'VW Champions' / internal contact |  | Y | [5 empty] | Y
2.1 | VW promo week - 1 of '5 things to know' each day |  | Y |  |  | Y
2.11 | Distribute stock of hard copy postcards / merch to key staff | Y | Y | [5 empty] | Y
2.12 | Email footer promoting VW site | Y | Y | Y |  | Y |  | Y | Y
2.13 | Posters in staff communal areas |  | Y | [5 empty] | Y | See Comms Hub
2.14 | Feature(s) in staff newsletter / comms |  | Y | [5 empty] | Y | PPL can assist with content
2.15 | Capture some early "user stories" | Y | Y | Y |  |  |  |  | Y
2.16 | Publish early user stories for staff to see |  | Y |  | Y | Y |  | Y
2.17 | Report usage levels and feedback to staff |  | Y |  | Y
2.18 | Update DP/PHB policy |  | Y | [5 empty] | Y
2.19 | Update DP/PHB processes |  | Y | [5 empty] | Y
3. Individuals
3.1 | Promote MyVW website as primary info source | Y
3.2 | VW engagement events | Y | [6 empty] | Y | Use std slides from Comms Hub
3.3 | Develop specific plans for any migration cohorts | Y |  |  |  | Y |  | Y | Y | eg PPCs, Managed Accounts
3.4 | Develop local benefits case (5 points) for individuals | [8 empty] | eg payroll, audit, phones etc
3.5 | 5 things for public to know about VW | Y |  |  |  |  | Y | Y |  | See Comms Hub - Key messages
3.6 | Launch VW on social media | Y | Y | Y |  |  | Y |  |  | Introducing our new approach
3.7 | Publish early user stories for individuals to see | Y |  |  |  |  | Y
3.8 | Develop welcome pack | Y | Y | Y |  |  |  |  | Y
3.9 | Scripts for staff / DPSS in early DP/PHB journey | Y | Y | Y |  |  |  |  | Y
3.1 | Attend co-production / user groups | Y | [6 empty] | Y | PPL and LA/ICB rep
3.11 | Insert in audit/review letter for slow adopters | Y | [6 empty] | Y
4. Partners (including DPSS)
4.1 | Initial meeting(s) with all partners (LA/ICB and PPL) |  |  | Y |  |  |  |  | Y
4.2 | Staff training at partner |  |  | Y |  |  |  |  | Y | PPL to support
4.3 | Collate FAQs/roles clarity document for partner usage |  |  | Y |  | Y |  |  | Y
4.4 | Distibute stock of hard copy postcards | Y |  | Y |  |  |  | Y | Y
4.5 | Review & update links on local 3rd sector sites to MyVW site | Y | Y | Y |  |  |  |  | Y
4.6 | Annual meeting with top 3 local partners |  |  | Y |  |  |  |  | Y | LA/ICB and PPL to attend
5. Providers
5.1 | Initial meeting with CME umbrella organisation | [7 empty] | Y
5.2 | Collate list of known providers to onboard |  |  |  |  | Y |  | Y | Y
5.3 | Signpost providers pages on MyVW website |  |  |  |  | Y |  | Y | Y
5.4 | Develop 5 local benefits messages for providers | [6 empty] | Y | Y | Paid on time, new market
5.5 | Engage with any local provider groups/forums | [7 empty] | Y | Use std slides from Comms Hub
5.6 | Include VW in any meetings with providers | [7 empty] | Y |  | Commg